## Tasks
Task ID | Epic | Sprint | Subject | Description | Owner | Points | Status | Blocked By | Start (wk) | End (wk) | Notes
TASK-0001 | 0 Foundations | S1 | Bootstrap monorepo with pnpm workspaces | Root package.json + pnpm workspaces for apps/services/packages; .nvmrc, .editorconfig, .gitignore; README with architecture diagram. |  | 2 | Pending |  | 1 | 1
TASK-0002 | 0 Foundations | S1 | CI baseline in GitHub Actions | Matrix jobs for mobile, core-java, pricing-py with lint/typecheck/test; dependency caching. |  | 3 | Pending | TASK-0001 | 1 | 2
TASK-0003 | 0 Foundations | S1 | Terraform skeleton for dev environment | Network, EKS or ECS, Mongo Atlas, Redis, S3 modules; remote state; make tf-plan-dev. |  | 5 | Pending | TASK-0001 | 1 | 2
TASK-0004 | 0 Foundations | S1 | Shared schemas package | Design, Floor, Room, Fixture, Estimate, RateItem schemas; codegen for TS/Java/Python. |  | 5 | Pending | TASK-0001 | 2 | 2 | Single source of truth
TASK-0501 | 0.5 Asset Intake | S2 | Create UI asset intake folders | brand/, figma/screens/, figma/components/ with README and naming conventions. |  | 1 | Pending | TASK-0001 | 2 | 2 | Drop Figma exports here
TASK-0502 | 0.5 Asset Intake | S2 | Asset-ingest pipeline script | scripts/assets-ingest.ts: PNG/SVG optimisation, @2x/@3x variants, manifest.json; pre-commit hook. |  | 3 | Pending | TASK-0501 | 2 | 3
TASK-0503 | 0.5 Asset Intake | S2 | Design-tokens sync to Tamagui theme | tokens.json -> theme.ts generator script. |  | 3 | Pending | TASK-0501 | 2 | 3
TASK-0504 | 0.5 Asset Intake | S2 | UI-generation task template | docs/design/_task_template.md + one example flow doc. |  | 1 | Pending | TASK-0501 | 2 | 3
TASK-0505 | 0.5 Asset Intake | S2 | Brand assets: logo, app icon, splash | Generate iOS/Android icon sets and splash from logo.svg; bootsplash wired. |  | 3 | Pending | TASK-0501 | 3 | 3 | Uses founder-supplied logo
TASK-1001 | 1 Auth & Onboarding | S3 | Firebase Auth + SDK integration | Email+Google+Apple providers; RN sign-in/up/reset screens built against Figma. |  | 5 | Pending | TASK-0501 | 3 | 4
TASK-1002 | 1 Auth & Onboarding | S3 | Core /auth/session and /me | Spring Boot auth-adapter verifies Firebase JWT; /me returns profile+role; RBAC annotations. |  | 5 | Pending | TASK-0004 | 3 | 4
TASK-1003 | 1 Auth & Onboarding | S3 | Onboarding flow (archetype + location) | Archetype picker, map/postcode location, optional budget, plot dimensions; PATCH /me/onboarding. |  | 5 | Pending | TASK-0502,TASK-1001 | 4 | 5
TASK-2001 | 2 Design Canvas | S4 | Skia canvas harness | react-native-skia pan+pinch-zoom, snap-to-grid 6in, ruler overlay, viewport transform utilities, perf harness. |  | 13 | Pending | TASK-0503 | 5 | 6 | Core of the product
TASK-2002 | 2 Design Canvas | S4 | Floor manager | Add/remove/reorder floors; tabs at canvas edge; per-floor state; archetype-defaults for floor height. |  | 5 | Pending | TASK-2001 | 6 | 6
TASK-2003 | 2 Design Canvas | S4 | Room primitive | Drag to draw rectangles, resize + corner handles, room-type picker, ceiling height, collision warning. |  | 8 | Pending | TASK-2002 | 6 | 7
TASK-2004 | 2 Design Canvas | S5 | Fixture tray (doors, windows, stairs) | Drag-drop on edges, snap with orientation lock, fixture spec sheet, stair primitive spanning floors. |  | 8 | Pending | TASK-2003 | 7 | 8
TASK-2005 | 2 Design Canvas | S5 | Finishes palette | Long-press room -> finishes sheet; finishes tied to rate-item SKUs. |  | 5 | Pending | TASK-2003 | 8 | 9
TASK-2006 | 2 Design Canvas | S5 | Design CRUD with auto-save | POST/GET/PUT /designs; 5s throttled auto-save; optimistic updates + conflict detection; offline queue. |  | 8 | Pending | TASK-0004,TASK-1002,TASK-2001 | 7 | 9
TASK-2007 | 2 Design Canvas | S5 | Undo/redo stack (50-step) | Canvas-level undo/redo via op-log; toolbar + gesture binding; bounded memory. |  | 8 | Pending | TASK-2001 | 9 | 10
TASK-2008 | 2 Design Canvas | S5 | Canvas performance hardening | Off-screen room virtualisation, GPU-layer pinning, draw-call batching, perf budget in CI. |  | 5 | Pending | TASK-2001,TASK-2003,TASK-2004 | 9 | 10
TASK-3001 | 3 Pricing & Scraper | S4 | FastAPI service scaffold | Uvicorn+Gunicorn, Motor, healthz, Dockerfile, OTel hooks. |  | 3 | Pending | TASK-0001,TASK-0002,TASK-0004 | 7 | 7
TASK-3002 | 3 Pricing & Scraper | S4 | Rate-item and rate-card-version collections | Mongo collections + indices; Pydantic models; seed script. |  | 3 | Pending | TASK-3001,TASK-0003 | 7 | 8
TASK-3003 | 3 Pricing & Scraper | S5 | One-off seed scrape script | Standalone CLI script: httpx+selectolax over 2-3 hardcoded sources; inserts 50-100 draft rate items. No plug-in engine, no cron, no Playwright. |  | 3 | Pending | TASK-3001 | 8 | 8 | Simplified per CTO
TASK-3004 | 3 Pricing & Scraper | S5 | Labour coefficient + regional multipliers | pricing.yaml with labour_coefficient=0.40; regional_multipliers collection seeded for top 20 cities. |  | 3 | Pending | TASK-3002 | 9 | 9
TASK-3005 | 3 Pricing & Scraper | S6 | /estimates:calculate endpoint | REST + gRPC; deterministic; returns full breakdown. |  | 8 | Pending | TASK-0004,TASK-3002,TASK-3004 | 10 | 11
TASK-3006 | 3 Pricing & Scraper | S6 | Admin rate-card endpoints | scrape-trigger/list/publish + item-level CRUD with override. |  | 5 | Pending | TASK-3002,TASK-3003 | 10 | 11
TASK-3007 | 3 Pricing & Scraper | S6 | Core <-> Pricing integration | EstimateOrchestrator -> Pricing gRPC; persists estimate with rateCardVersionId. |  | 5 | Pending | TASK-2006,TASK-3005 | 11 | 12
TASK-3008 | 3 Pricing & Scraper | S6 | Admin rate-entry UI | Table view with search/filter, inline edit, CSV bulk import, audit log. Lives in admin console (Epic 7); interim route in mobile app. |  | 5 | Pending | TASK-3006 | 11 | 12 | Primary rate-update surface
TASK-4001 | 4 Estimate UX | S6 | Estimate screen | Materials, 40% labour line, regional premium, overhead, grand total; category drill-down. |  | 5 | Pending | TASK-0502,TASK-3007 | 11 | 12
TASK-4002 | 4 Estimate UX | S7 | PDF estimate export | Branded PDF via Core export endpoint; SES email; Indicative MVP disclaimer. |  | 5 | Pending | TASK-4001 | 12 | 13
TASK-4003 | 4 Estimate UX | S7 | Share link | Signed, time-bounded share URL; revokable. |  | 3 | Pending | TASK-4002 | 13 | 13
TASK-5001 | 5 Launch | S7 | Load test core + pricing | k6 to 200 rps on /estimate; report P50/P95/P99 + error rate. |  | 3 | Pending | TASK-3007 | 13 | 14
TASK-5002 | 5 Launch | S7 | Security review | MASVS checklist, pen test of auth + admin, Dependabot. |  | 5 | Pending | TASK-1002,TASK-3006 | 13 | 14
TASK-5003 | 5 Launch | S7 | App Store + Play Store submissions | Signed builds, privacy manifest, data-safety form, TestFlight/Play closed testing. |  | 5 | Pending | TASK-5002 | 14 | 15
TASK-5004 | 5 Launch | S7 | Observability & on-call | Datadog dashboards, error budgets, PagerDuty schedule, runbooks. |  | 3 | Pending | TASK-3001,TASK-1002 | 14 | 15
TASK-6001 | 6 Phase 2 | S8+ | PDF/DOCX ingestion pipeline | pdfplumber+camelot+OCR fallback + LLM mapping + human review queue. |  | 13 | Pending | TASK-3006 | 16 | 19 | Requires source doc
TASK-6002 | 6 Phase 2 | S8+ | Per-trade labour decomposition | Replace 40% flat with mason/plumber/electrician/painter/tiler/carpenter breakdown. |  | 8 | Pending | TASK-6001 | 19 | 21
TASK-6003 | 6 Phase 2 | S8+ | Estimate calibration job | Offline job comparing estimates vs real quotes; tunes coefficients. |  | 5 | Pending | TASK-6002 | 21 | 22
TASK-7001 | 7 Admin Monitoring | S9+ | Admin console scaffold (Next.js) | apps/admin-web Next.js 14, NextAuth+Firebase, admin-only guard, nav shell. Staging-only until launched. |  | 5 | Deferred | TASK-1001,TASK-1002 | 22 | 23 | Post-launch
TASK-7002 | 7 Admin Monitoring | S9+ | Usage-limits dashboard | Per-tier rate limits enforced in core; dashboard of breaches, top-N users, time-series volume. |  | 5 | Deferred | TASK-7001,TASK-5004 | 23 | 24
TASK-7003 | 7 Admin Monitoring | S9+ | Customer support inbox | In-app 'Need help?' form; admin inbox with reply, status transitions, email notifications; audit-logged. |  | 5 | Deferred | TASK-7001 | 23 | 24
TASK-7004 | 7 Admin Monitoring | S3+ | Instrumentation hooks (alongside MVP) | Event bus emits user.signup, design.created, estimate.requested, pdf.exported, support.submitted to 'events' (TTL 90d); Grafana views wired. |  | 3 | Pending |  | 3 | 15 | Built during Epics 1-5
TASK-7005 | 7 Admin Monitoring | S9+ | Admin audit log | Every admin action to admin_audit_log; filterable view; 7-year retention. |  | 3 | Deferred | TASK-7001,TASK-3008 | 24 | 24
TASK-8001 | 8 AI Layout Generator | S10+ | Layout-generation service scaffold | services/layout-py FastAPI service: healthz, /v1/layouts:generate stub, OTel hooks, Dockerfile, k8s manifest. Python 3.12 + Pydantic v2. |  | 5 | Deferred | TASK-0001,TASK-0002 | 25 | 25 | Vastu-compliant constraints
TASK-8002 | 8 AI Layout Generator | S10+ | Constraint + rule engine | Hard constraints (overlap, min room sizes, reachability, stairs) + Vastu soft constraints (directions per room type) + natural light + adjacency rules. python-constraint or OR-Tools. Tunable weights via pricing-style YAML. |  | 13 | Deferred | TASK-8001,TASK-0004 | 25 | 27 | Core of the epic
TASK-8003 | 8 AI Layout Generator | S10+ | Layout Generator UI | RN screens: input form (plot width/depth/unit, archetype, #bedrooms, #bathrooms, Vastu mode, budget hint) -> candidate list (1-3 ranked) with per-constraint score breakdown -> preview. |  | 8 | Deferred | TASK-8002,TASK-2001 | 27 | 28
TASK-8004 | 8 AI Layout Generator | S10+ | Layout <-> Canvas handoff | Materialise a chosen candidate as a Design Document, open in canvas in edit mode; round-trip tested end-to-end. |  | 5 | Deferred | TASK-8003,TASK-2006 | 28 | 29
TASK-8005 | 8 AI Layout Generator | S10+ | Layout feedback loop | User 'not usable' flag with reason; writes to layout_feedback; admin view in Phase-7 console; weekly summary export for constraint-weight tuning. |  | 3 | Deferred | TASK-8003,TASK-7001 | 29 | 29

## Summary
Build Buddy (codename: Bob the Builder) - Sprint Tracker Summary
Metric | Value
Total tasks
Points planned
Points done
Points in progress
Points blocked
% complete (by points)
By Epic
Epic | Tasks | Points | Done pts | In Progress pts
0 Foundations
0.5 Asset Intake
1 Auth & Onboarding
2 Design Canvas
3 Pricing & Scraper
4 Estimate UX
5 Launch
6 Phase 2
7 Admin Monitoring
8 AI Layout Generator

## README
Build Buddy - Sprint Tracker README (project codename: Bob the Builder)
Use this workbook as the source of truth for sprint planning.
Columns:
Task ID - Stable identifier; also used as the heading in the Task List markdown.
Epic - Grouping; feeds the Summary breakdown.
Sprint - Target 2-week sprint (S1 = weeks 1-2, S2 = weeks 3-4, ...).
Subject - Short imperative title.
Description - What needs to be done; enough to schedule in Claude Code.
Owner - Assignee name (fill in once the team is staffed).
Points - Fibonacci estimate; update as scope firms up.
Status - Pending / In Progress / Blocked / Done / Deferred (dropdown).
Blocked By - Comma-separated Task IDs that must finish first.
Start / End - Calendar week (1-indexed from project kickoff).
Notes - Free-form.
Conventions:
- Reuse a task ID for follow-ups by appending a letter (TASK-2001a).
- When status goes to Done, the Summary sheet updates automatically.
- Blocked tasks should always have a Notes entry explaining why.
Scheduling in Claude Code:
1. Open Bob_the_Builder_Task_List.md (kept under the project codename).
2. Copy the section for the Task ID you are working on.
3. In Claude Code, run /task and paste the section as the prompt.
4. When the PR merges, flip the status here to Done.